## README
SwiftLoan — Consolidated Compliance Evidence Pack & Claims Matrix
Purpose: single tracking workbook for ISO/IEC 27001:2022 + SOC 2 audits and DPDP/RBI compliance.
Sheets:
• Claims Matrix — marketing/compliance claims, bucketed (self-declarable / cert-required / prohibited).
• Control Evidence — the C1–C14 findings, current status, file:line evidence, remediation.
• Remediation Tracker — P0–P3 action items with owner/status/target date.
• Framework Coverage — DPDP / RBI DLG / RBI KYC / CICRA / CERT-In / IT-Act / ISO / SOC 2 summary.
• Live Control Status — AUTO-GENERATED by scripts/compliance/compliance_sync.py (do not hand-edit).
Maintenance: on every push to main, the compliance-sync GitHub Action refreshes 'Live Control Status'
and flags the six documents for review when monitored source files change.

## Claims Matrix
Claim | Bucket | Framework / Basis | Can promote? | Evidence required | Status | Owner
DPDP Act 2023 compliant | Self-declarable | DPDP Act 2023 | Yes, once implemented + evidenced | Consent records, DSAR flows, RoPA, breach process | Planned | DPO
Compliant with IT Act §43A / SPDI Rules | Self-declarable | IT Act 2000 / SPDI 2011 | Yes | Security policy, encryption evidence | Planned | DPO
Aligned with RBI Digital Lending Guidelines (as LSP for regulated lenders) | Self-declarable | RBI DLG 2022 | Yes — must name RE partnership | LSP-RE agreement, KFS, grievance officer | Planned | Compliance
Consent-based data sharing; CICRA-compliant credit checks | Self-declarable | CICRA 2005 | Yes | Consent artifacts before bureau pull | Open | Backend
Data encrypted in transit and at rest; PAN tokenized/masked | Self-declarable | ISO A.8.24 / SOC2 C1.1 | Yes, once C1 fixed | TLS config, KMS, PAN vault | Open | DevOps
Data stored & processed in India (residency) | Self-declarable | RBI DLG / DPDP | Yes, once enforced | Region config, DPA | Planned | DevOps
CERT-In-aligned incident response (6-hr reporting) | Self-declarable | CERT-In 2022 | Yes | IR runbook, log retention 180d | Planned | Security
No dark patterns; transparent all-in APR (KFS) | Self-declarable | CP Act / CCPA guidelines | Yes | KFS UI, UX review | Partial | Product
ISO/IEC 27001:2022 certified | Certification required | ISO 27001 | Only AFTER accredited audit | Certificate from accredited body | Not started | Security
SOC 2 Type II | Certification required | AICPA TSC | Only AFTER auditor report | Type II report (3-12 mo evidence) | Not started | Security
PCI-DSS compliant | Certification required (if cards) | PCI-DSS | Only if card data + QSA/SAQ | SAQ / QSA attestation | N/A unless card data | Security
Independently VAPT / penetration-tested | Certification/audit required | — | After 3rd-party test | Dated VAPT report | Not started | Security
RBI-approved / RBI-licensed app | PROHIBITED | — | NO — RBI licenses REs, not apps/LSPs | n/a — do not claim | Do not use | Legal
100% secure / hack-proof / bank-grade | PROHIBITED | — | NO — misleading | n/a | Do not use | Legal

## Control Evidence
ID | Finding / Control | Current status | Evidence (file:line) | ISO 27001:2022 | SOC 2 TSC | Remediation | Priority
C1 | PAN stored plaintext & duplicated | Open | schema.prisma:62,171 | A.8.24, A.8.11 | CC6.1, C1.1 | Tokenize/encrypt PAN; de-duplicate | P1
C2 | Sensitive values leak to Ello voice AI | Open | voice/actionRegistry.ts:204; screenGraph.ts:207 | A.8.11, A.5.34 | C1.1, P4 | Redact sensitive values from page_context | P0
C3 | Fixed OTP 123456 accepted in prod | Open | lib/crypto.ts:9-11; render.yaml | A.8.5 | CC6.1 | Disable DEMO_LOGIN in prod | P0
C4 | Default admin admin123 seeded | Open | seed.ws4.ts:74,82-83 | A.8.5, A.5.17 | CC6.1 | Remove default creds; add MFA | P0
C5 | Real Ello API key committed | Open | render.yaml:53; website/js/voice-widget.js:17 | A.8.24, A.5.19 | CC6.1, CC9.2 | Rotate; secrets manager; purge history | P0
C6 | Fail-open JWT/admin secrets | Open | config/env.ts:12-13 | A.8.9, A.8.24 | CC6.1, CC8.1 | Remove dev fallbacks; fail closed | P0
C7 | CORS fully open; limited rate-limiting | Open | app.ts:27 | A.8.20, A.8.23 | CC6.6 | Allow-list CORS; rate-limit all routes | P1
C8 | Unvalidated tracking metadata (PII sink) | Open | tracking.routes.ts:30,67 | A.8.12 | C1.2 | Allow-list + scrub PII | P2
C9 | Orphan PII never purged; no retention TTL | Open | AnonymousLead/ContextSession/Notification | A.5.33, A.8.10 | P4 | Retention TTL + purge jobs | P2
C10 | No DSAR beyond self-delete; AuditLog unused | Open | users.routes.ts:91; AuditLog model | A.8.15, A.5.34 | CC7.1, P5 | DSAR APIs; write AuditLog | P2
C11 | Admin tokens in localStorage (XSS) | Open | admin/src/lib/api.ts:12-22 | A.8.3, A.8.5 | CC6.1 | httpOnly cookies + RBAC | P1
C12 | No DB encryption-at-rest / residency / DPA | Open | infra / render.yaml | A.8.24, A.5.19, A.5.23 | CC6.1, A1.2 | TDE, India region, DPAs | P1
C13 | Voice transport ws://,http:// cleartext | Open | voice/config.ts | A.8.24, A.8.20 | CC6.7, C1.1 | Force wss:// / https:// | P0
C14 | No client-side secure input / masking | Open | basicpan.tsx / KYC screens | A.8.11 | C1.1 | secureTextEntry + masking | P1
K1 | Passwords bcrypt (GOOD) | Implemented | lib/crypto.ts:4 | A.5.17 | CC6.1 | Keep | -
K2 | OTP/refresh tokens hashed (GOOD) | Implemented | schema:94,107 | A.5.17, A.8.24 | CC6.1 | Keep | -
K3 | Aadhaar/bank last-4 only (GOOD) | Implemented | schema:63,265 | A.8.11 | C1.1, P4 | Keep | -
K4 | iOS ATS enforced (GOOD) | Implemented | Info.plist:29-35 | A.8.24 | CC6.7 | Keep | -
K5 | User hard-delete w/ cascade (GOOD) | Implemented | users.routes.ts:91 | A.8.10 | P5 | Extend to orphan PII | -

## Remediation Tracker
Action ID | Priority | Task | Owner | Effort | Status | Target date | Linked findings | Done-when
P0-1 | P0 | Rotate & purge committed Ello key; secrets manager | DevOps+Web | 0.5d | Not started |  | C5 | No ak_ in tracked files; key rotated
P0-2 | P0 | Disable DEMO_LOGIN/fixed-OTP in prod | Backend+Mobile | 0.5d | Not started |  | C3 | Prod rejects 123456
P0-3 | P0 | Remove default admin creds; add MFA | Backend+Web | 1-2d | Not started |  | C4 | No default password; MFA enforced
P0-4 | P0 | Redact sensitive values from voice page_context | Mobile | 1-2d | Not started |  | C2 | No PAN leaves device to Ello
P0-5 | P0 | Fail-closed secrets (no dev fallback) | Backend | 0.5d | Not started |  | C6 | Boot fails without real secrets
P1-1 | P1 | Tokenize/encrypt PAN + de-duplicate | Backend | 3-5d | Not started |  | C1 | No plaintext PAN column
P1-2 | P1 | DB encryption at rest + backups (India) | DevOps | 2-3d | Not started |  | C12 | TDE on; India region
P1-3 | P1 | CORS allow-list + rate-limit/WAF all routes | Backend | 1-2d | Not started |  | C7 | Only approved origins; all routes throttled
P1-4 | P1 | Wire consent + enforce before partner/CIBIL share | Backend+Mobile | 3-5d | Not started |  | C8,C10 | No share without recorded consent
P1-5 | P1 | Admin tokens httpOnly + RBAC | Web+Backend | 2-3d | Not started |  | C11 | Tokens not JS-readable; RBAC on PII
P1-6 | P1 | Secure input + PAN masking | Mobile+Web | 1-2d | Not started |  | C14,C1 | PAN masked in UI/logs
P1-7 | P1 | Voice consent-gate + wss/https only | Mobile | 1-2d | Not started |  | C13,C2 | No cleartext voice; opt-in required
P2-1 | P2 | Retention TTL + purge jobs | Backend | 2-3d | Not started |  | C9 | Orphan PII expires
P2-2 | P2 | DSAR APIs (access/correct/export/erase) | Backend | 3-5d | Not started |  | C10 | Full self-service DSAR incl. orphan PII
P2-3 | P2 | Write AuditLog on PII access | Backend | 2d | Not started |  | C10 | PII access auditable
P2-6 | P2 | Governance: RoPA, DPIA, DPO, breach runbook | Compliance | ongoing | Not started |  | C12 | Docs approved; officer named
P2-7 | P2 | Sign DPAs (Ello, lenders, host) | Legal | ongoing | Not started |  | C12,C5 | Executed DPAs on file
P3-1 | P3 | Independent VAPT | Security | 1-2wk | Not started |  | all | Report; criticals fixed
P3-2 | P3 | ISO 27001 + SOC 2 audits | Security | quarter+ | Not started |  | all | Certificate/report obtained
P3-3 | P3 | Legal sign-off on marketing claims | Legal+Mktg | ongoing | Not started |  | claims | Claims substantiated & approved

## Framework Coverage
Framework | Type | Scope / Applicability | Primary controls in these docs | Status
ISO/IEC 27001:2022 | Certifiable ISMS | Whole platform | SoA (93 controls), risk register, ISMS clauses 4-10 | Readiness / Planned
SOC 2 (AICPA TSC) | Attestation | Security, Confidentiality, Privacy, Availability | CC1-CC9 + A1/C1/PI1/P mapping | Readiness / Planned
DPDP Act 2023 | Law (India) | All personal data | Consent, DSAR, retention, breach, security | Partial / Planned
RBI Digital Lending Guidelines 2022 | Regulation | LSP/DLA operations | Data-min, localization, KFS, grievance | Partial / Planned
RBI KYC / CKYC | Regulation | KYC/identity | PAN/Aadhaar handling, masking | Partial
CICRA 2005 | Law | Credit bureau pulls | Consent before soft-pull | Open
CERT-In Directions 2022 | Directive | Incident/logging | 6-hr breach report, 180d logs, NTP | Planned
IT Act §43A / SPDI 2011 | Law | Sensitive personal data | Reasonable security, encryption | Partial
PCI-DSS | Standard (conditional) | Only if card data handled | N/A unless card rails used | N/A

## Live Control Status
Auto-generated · commit 5c1deff · 2026-08-04 16:44 UTC
ID | Control | Status | ISO 27001:2022 | SOC 2 TSC | Evidence | Remediation
C1 | PAN encrypted/tokenized at rest (not plaintext) | Open | A.8.24, A.8.11 | CC6.1, C1.1 | server/prisma/schema.prisma:62,171 | Tokenize/field-encrypt PAN; de-duplicate to one source.
C2 | Voice page_context redacts sensitive field values | Open | A.8.11, A.5.34 | C1.1, P4 | src/voice/actionRegistry.ts:204; src/voice/screenGraph.ts:207 | Redact sensitive values from page_context/read_screen.
C3 | Fixed demo-OTP disabled in production | Open | A.8.5 | CC6.1 | render.yaml DEMO_LOGIN; lib/crypto.ts:9-11 | Set DEMO_LOGIN=false in prod; remove client bypass.
C4 | No default/shared admin credential | Open | A.8.5, A.5.17 | CC6.1 | server/prisma/seed.ws4.ts:74,82-83 | Remove admin123 seed; force reset + MFA.
C5 | No live API key committed to source | Open | A.8.24, A.5.19 | CC6.1, CC9.2 | render.yaml:53; website/js/voice-widget.js:17 | Rotate key; move to secrets manager; purge history.
C6 | Secrets fail-closed (no dev fallback) | Open | A.8.9, A.8.24 | CC6.1, CC8.1 | server/src/config/env.ts:12-13 | Remove dev-access/dev-refresh fallbacks; fail on boot.
C7 | CORS restricted to allow-list | Open | A.8.20, A.8.23 | CC6.6 | server/src/app.ts:27 | Replace open cors() with an origin allow-list.
C11 | Admin tokens not in localStorage (httpOnly) | Open | A.8.3, A.8.5 | CC6.1 | admin/src/lib/api.ts:12-22 | Move admin tokens to httpOnly cookies.
C13 | Voice transport TLS-only (no ws://,http://) | Open | A.8.24, A.8.20 | CC6.7, C1.1 | src/voice/config.ts | Force wss:// and https:// for voice transport.
G5 | Secret scanning in CI (gitleaks) | Implemented | A.8.8, A.8.4 | CC7.1 | .github/workflows/security-scan.yml | Keep gitleaks in CI; enable GitHub push protection.
G6 | SAST in CI (CodeQL) | Implemented | A.8.25, A.8.28 | CC8.1 | .github/workflows/security-scan.yml | Keep CodeQL; triage findings.
G7 | Dependency/SCA scanning (Dependabot + npm audit) | Implemented | A.8.8 | CC7.1 | .github/dependabot.yml | Keep Dependabot; act on advisories.
G8 | Mandatory code-owner review | Implemented | A.8.4, A.8.32 | CC8.1 | CODEOWNERS | Enable 'Require Code Owner review' in branch protection.
G9 | Vulnerability disclosure policy | Implemented | A.5.5, A.5.24 | CC2.3 | SECURITY.md | Keep current; staff the security mailbox.
G10 | PR governance (security/compliance checklist) | Implemented | A.8.32 | CC8.1 | .github/pull_request_template.md | Keep; enforce checklist in review.
G11 | IP / licensing clarity | Implemented | A.5.32 | CC1.1 | LICENSE | Keep proprietary notice current.