## README
SwiftLoan — SDLC & Change-Management Tracker (SL-CMP-07)
Live evidence of a controlled Secure SDLC for ISO/IEC 27001:2022 (A.8.25/26/28/29/31/32) and SOC 2 (CC8.1).
Every change flows through 8 gates: Created > Reviewed > Tasks defined > Assigned > Implemented > Tested > Approved > Pushed/Merged.
Segregation of duties: implementer != approver/merger (enforced via GitHub PR review).
Sheets:
Change Log - real work items / PRs (#2-#11) through the 8 lifecycle stages, with commit/PR evidence.
Security Remediation - C1-C14 / P0-P3 findings at their current SDLC stage (pipeline for outstanding security work).
Approvals Register - formal change/release/security/compliance sign-offs.
Stage Legend - stage definitions + ISO/SOC 2 control mapping.
Every ID resolves to a Git commit hash and/or GitHub PR number = independently verifiable.
Document ownership — Product Owner: Sridhar Muppidi ¦ Product Head: Sachin Tulla ¦ Technical Head: Sachin Tulla ¦ Head of Engineering: Hari PS ¦ Security Head: Anil M

## Change Log
ID | Work item | Type | Req / Control ref | Created | Reviewed | Tasks defined | Assigned to (implementer) | Implemented (branch / commit) | Tested (evidence) | Approved by | Pushed / Merged (PR / commit) | Status
CL-01 | Initial platform: RN app (design-port) + backend scaffold | Feature | PRD FR-onboarding/funnel | 2026-07-27 | Yes | Yes | SwiftLoan Dev | main / a9f1784+ | Jest suite | Release mgr | main | Merged
CL-02 | Ello voice-command layer (talk to drive the app) | Feature | PRD FR-voice | 2026-07-27 | Yes | Yes | charan.rallabandi | ello_sdk_2707 / 86013f2 | Manual QA + Jest | Release mgr | PR #6 / c609249 | Merged
CL-03 | Admin dashboard + tracking backend + marketing website | Feature | PRD FR-admin/tracking | 2026-07-27 | Yes | Yes | charan.rallabandi | branch / 6845fc6 | Build + smoke | Release mgr | PR #4 | Merged
CL-04 | Mobile fire-and-forget tracking side-effects | Feature | PRD FR-tracking | 2026-07-22 | Yes | Yes | veerendra.bhimireddy | worktree-add-tracking | Jest | Release mgr | PR #2 | Merged
CL-05 | Website / dashboard converted to Next.js + i18n | Feature | PRD FR-website | 2026-07-28 | Yes | Yes | veerendra.bhimireddy | Website/dashboard | Build | Release mgr | PR #4 / #8 | Merged
CL-06 | Voice-agent fixes: context timing, date picker, scroll, icons | Fix | Doc04 TC-voice | 2026-07-28 | Yes | Yes | charan.rallabandi | ello-sdk-2807 / 1a78ef7 | Manual QA | Release mgr | PR #6 | Merged
CL-07 | In-app voice copilot system prompt | Feature | PRD FR-voice | 2026-07-30 | Yes | Yes | charan.rallabandi | apk-1.5.6 / a1c44d9 | Prompt review | Release mgr | PR #7 | Merged
CL-08 | Real Twilio OTP login + screen drop-off tracking (removes demo OTP) | Security/Fix | C3; Doc04 TC-auth | 2026-07-28 | Yes | Yes | veerendra.bhimireddy | OTP / c784b3a,81c45ee | Manual + Jest | Pending | PR #5 (open) | In review
CL-09 | WebRTC transport for voice communication | Feature | PRD FR-voice | 2026-07-30 | Yes | Yes | charan.rallabandi | apk-1.5.6 / a9d13f4 | Manual QA | Release mgr | PR #9 | Merged
CL-10 | Ello widget on website-next + repo tooling fixes | Feature | PRD FR-website | 2026-07-31 | Yes | Yes | charan.rallabandi | apk-1.5.6 / 6ac4a7d | Build | Release mgr | PR #10 | Merged
CL-11 | Name in-app copilot 'Ruby' + prompt wording refinement | Change | PRD FR-voice | 2026-07-31 | Yes | Yes | Sachin Tulla | main / 8aa2ab5,e2955c1 | Prompt review + live check | Release mgr | main | Merged
CL-12 | Production deployment GitHub Actions workflow | Infra | ISO A.8.31/A.8.32 | 2026-08-03 | Yes | Yes | charan.rallabandi | main / df5d2ea | Workflow dry-run | Release mgr | main | Merged
CL-13 | Upshot SDK analytics (mobile + web) | Feature | PRD FR-tracking | 2026-08-03 | Yes | Yes | veerendra.bhimireddy | branch / e854e18 | Build | Release mgr | main | Merged
CL-14 | Voice agent roles + context management | Feature | PRD FR-voice | 2026-08-04 | Yes | Yes | veerendra.bhimireddy | branch / 1134fe0 | Manual QA | Release mgr | Website/dashboard | Merged
CL-15 | Compliance documentation suite + automated compliance-sync | Doc/Security | Docs 01-06; ISO/SOC2 | 2026-08-04 | Yes | Yes | Sachin Tulla | sachin_dev / 6c1348c | Doc review + sync engine run | Pending | PR #11 (open) | In review
CL-16 | Render TAD Mermaid diagrams to real images | Doc | Doc02 | 2026-08-04 | Yes | Yes | Sachin Tulla | sachin_dev / e0b5e25 | Visual verify | Pending | PR #11 (open) | In review
CL-17 | Embed current + target architecture diagrams in docs | Doc | Doc02/03 | 2026-08-04 | Yes | Yes | Sachin Tulla | sachin_dev / 2a082f8 | Visual verify | Pending | PR #11 (open) | In review

## Security Remediation
ID | Finding / Action | Priority | Control ref (ISO / SOC2) | Created | Reviewed | Tasks defined | Assigned to (role) | Implemented | Tested | Approved | Pushed | Status
R-C5 | Rotate & purge committed Ello key; secrets manager | P0 | A.8.24 / CC6.1 | Yes | Yes | Yes | DevOps | No | No | No | No | Backlog - assigned
R-C3 | Disable DEMO_LOGIN / fixed OTP in prod | P0 | A.8.5 / CC6.1 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned
R-C4 | Remove default admin creds; add MFA | P0 | A.8.5 / CC6.1 | Yes | Yes | Yes | Backend+Web | No | No | No | No | Backlog - assigned
R-C2 | Redact sensitive values from voice page_context | P0 | A.8.11 / C1.1 | Yes | Yes | Yes | Mobile | No | No | No | No | Backlog - assigned
R-C6 | Fail-closed secrets (no dev fallback) | P0 | A.8.9 / CC6.1 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned
R-C1 | Tokenize/encrypt PAN + de-duplicate | P1 | A.8.24 / C1.1 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned
R-C12 | DB encryption at rest + backups (India) | P1 | A.8.24 / A1.2 | Yes | Yes | Yes | DevOps | No | No | No | No | Backlog - assigned
R-C7 | CORS allow-list + rate-limit all routes | P1 | A.8.20 / CC6.6 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned
R-C11 | Admin tokens httpOnly + RBAC | P1 | A.8.3 / CC6.1 | Yes | Yes | Yes | Web+Backend | No | No | No | No | Backlog - assigned
R-C13 | Voice transport wss/https only | P0 | A.8.24 / CC6.7 | Yes | Yes | Yes | Mobile | No | No | No | No | Backlog - assigned
R-C14 | Secure input + PAN masking (client) | P1 | A.8.11 / C1.1 | Yes | Yes | Yes | Mobile | No | No | No | No | Backlog - assigned
R-C8 | Allow-list + scrub PII from tracking metadata | P2 | A.8.12 / C1.2 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned
R-C9 | Retention TTL + purge jobs (orphan PII) | P2 | A.8.10 / P4 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned
R-C10 | DSAR APIs + write AuditLog on PII access | P2 | A.8.15 / P5 | Yes | Yes | Yes | Backend | No | No | No | No | Backlog - assigned

## Approvals Register
Approval ID | Item | Type | Approver (role) | Date | Decision | Reference
AP-01 | PR #2 Mobile tracking | Change/Merge | Release Manager | 2026-07-22 | Approved & merged | PR #2
AP-02 | PR #4 Website/dashboard | Change/Merge | Release Manager | 2026-07-28 | Approved & merged | PR #4
AP-03 | PR #6 Voice-agent fixes | Change/Merge | Release Manager | 2026-07-28 | Approved & merged | PR #6
AP-04 | PR #7 In-app voice prompt | Change/Merge | Release Manager | 2026-07-30 | Approved & merged | PR #7
AP-05 | PR #9 WebRTC transport | Change/Merge | Release Manager | 2026-07-30 | Approved & merged | PR #9
AP-06 | PR #10 Website-next widget | Change/Merge | Release Manager | 2026-07-31 | Approved & merged | PR #10
AP-07 | Prod deployment workflow | Release | Release Manager | 2026-08-03 | Approved | df5d2ea
AP-08 | PR #5 Twilio OTP (removes demo OTP) | Change/Security | Security Lead |  | PENDING review | PR #5
AP-09 | PR #11 Compliance documentation suite | Compliance | DPO / Compliance |  | PENDING review | PR #11
AP-10 | Security remediation P0 batch sign-off | Security | CISO |  | PENDING (post-implementation) | Backlog R-C*
AP-11 | ISO 27001 / SOC 2 readiness sign-off | Compliance | CISO / DPO |  | PENDING | Docs 01-06

## Stage Legend
# | Stage | Exit-gate evidence | ISO 27001:2022 | SOC 2 TSC
1 | Created | Item logged: ID, date, requirement/control ref | A.8.26 | CC3.2
2 | Reviewed | Triaged, risk-assessed, prioritized, acceptance criteria | A.8.25 | CC3.2, CC5.1
3 | Tasks defined | Task breakdown recorded | A.8.25 | CC5.1
4 | Assigned | Owner + reviewer/approver assigned (SoD) | A.5.3 | CC5.3
5 | Implemented | Commit(s) on feature branch; secure coding | A.8.28, A.8.31 | CC8.1
6 | Tested | Unit/integration/security tests; CI status | A.8.29 | CC8.1
7 | Approved | Peer review + approval by a different person | A.8.32, A.5.3 | CC8.1, CC5.3
8 | Pushed / Merged | Merged to main; deployed via workflow | A.8.32, A.8.31 | CC8.1